## Sheet1
Speech Authentication System	Week 1					Week 2					Week 3					Week 4					Week 5					Week 6					Week 7					Week 8					Week 9					Week 10
	Dec 1-5					Dec 6-10					Dec 13-17					Dec 20-24					Jan 3-7					Jan 10-14					Jan 17-21					Jan 24-28					Jan 31- Feb 3					Feb 6-10
Starting with the Project
-Group formation
-Project ideas with feedback
Group Presentation
Building the Project
- Coding the GUI and the main software
- Assembling hardware
Testing and Debugging
In-class Project Days
Final project presentation